## Dashboard
BoldSign Link Authority Plan 2026
Prepared August 17, 2026. Owner: Nihal Mohamed Ali. Reviewer: Meikandan. Companion to the v2 patch document.
How to use this workbook
- Every tab is a standalone table. Fill yellow cells only. Yellow means you supply the value.
- Workstream A is coverage. Workstream B is authority. Both run in parallel from week 1.
- The status counts below update automatically as you change the Status column on the Tracker tab.
- The three dropped items (Scribd, Issuu, AppSumo) stay in the Tracker marked Dropped so nobody re-adds them.
- No em dashes anywhere by request. Colours follow the BoldSign brand palette.
Live status rollup
Status | Count | Stream A count | Stream B count
Not started | 46 | 34 | 12
Submitted | 0 | 0 | 0
Live | 0 | 0 | 0
Needs review | 0 | 0 | 0
Rejected | 0 | 0 | 0
Dropped | 3 | 3 | 0
Total tracked | 49 | 37 | 12
Tab guide
Tab | What it is | Action needed
Findings | The 17 issues found in the two source files |  | Read first
Tracker | All 49 rows: 46 active plus 3 dropped, pre-populated |  | Fill Status, Owner, dates, URLs as you go
Baseline and KPIs | Metrics to prove the programme worked |  | Fill baseline column before week 1
Competitor Gap | Referring domain gap vs competitors |  | Fill after Semrush units are restored
Claims Control | Version control for pasted facts |  | Fill owner and review dates
Bio Library | Six distinct bios and where each goes |  | Copy exact, do not blend angles
Priority Order | Revised sequence, both streams |  | Follow top to bottom
Schedule | Honest capacity model and review gates |  | Adjust dates, not the sequence
UTM Convention | Exact tracking pattern and examples |  | Build the GA4 filter before week 1
Do Not Do | 14 non-negotiable prohibitions |  | Read before any outreach

## Findings
Findings: what needs to improve
17 issues across both source files, highest severity first.
# | Issue | Severity | Where
1 | Two files share the same H1 and roughly 95 percent identical body. The Guide is a superset of the DA-Action-Plan file. Version drift risk. | High | Both files
2 | Titled a Domain Authority plan, but around 20 of 28 actions are nofollow or UGC surfaces. Almost nothing passes link equity. | High | Whole plan
3 | No baseline, no KPI, no success criteria. Cannot prove the programme worked. | High | Goal block
4 | No referring domain gap analysis against competitors. The plan benchmarks profile presence, never link sources. | High | Missing
5 | Syncfusion.com and subdomains still in the disavow file. The single highest value zero cost authority action, and it is absent. | High | Missing
6 | No earned or editorial link workstream at all. No digital PR, no unlinked mention reclamation, no broken link building, no linkable data assets. | High | Missing
7 | Hardcoded facts pasted into 28 profiles with no version control. Gartner Digital Markets penalises pricing inaccuracy. | Medium | Assets block
8 | 20 paste-ready bios are the same 8 phrases reshuffled. Reads as boilerplate to directories and to language models. | Medium | All 28 actions
9 | Eversign and XodoSign listed as separate competitors. Same product post rebrand. Xome and Maverick still unflagged as notary services. | Medium | Competitor block
10 | SlideShare, Scribd, Issuu sit at priority 5, 6, 7. Near zero value in 2026, all nofollow, same PDF three times. | Medium | Phase 1
11 | Google Workspace Marketplace ranked 26 of 28, despite being the confirmed highest priority marketplace gap. Weeks of lead time means it must start now. | Medium | Priority table
12 | No anchor text plan, no target URL distribution. Everything points at homepage or pricing. | Medium | Missing
13 | AppSumo lifetime deal positioning would break the unlimited envelope story. Flagged too softly. | Medium | Action 28
14 | Missing surfaces: package registries, Microsoft AppSource, MCP registries beyond two, a real Product Hunt launch, Trustpilot, Gartner Peer Insights, Tekpon, SaaSworthy. | Medium | Missing
15 | No owner column, no dates, no capacity math. 28 actions in 4 weeks is not achievable solo. | Medium | Schedule
16 | F5Bot workflow overlaps the live Reddit calendar with no cross-reference. | Low | Action 22
17 | Verified URL section has no re-verification date or cadence. | Low | Guide only

## Tracker
Master tracker: 46 actions plus 3 dropped
Fill yellow columns as you execute. Status drives the Dashboard rollup. Dropped rows stay for the record.
Action ID | Stream | Platform / Action | Difficulty | Priority | Status | Owner | Target Date | Live URL | Login Owner | Category Used | Bio Angle Used | Competitors Benchmarked | Link Type Verified | Review Count | UTM Content Tag | Date Submitted | Date Live | Next Action | Notes
A00 | B | Syncfusion disavow removal and cross-links | Very easy | 0 | Not started | [5 empty] | n/a | n/a | do-follow |  | a00 |  |  | Remove syncfusion.com from disavow then re-audit all entries | Highest value item in the plan. Zero cost.
B01 | B | Referring domain gap analysis | Easy | 1 | Not started | [5 empty] | n/a | Tier 1 all | n/a |  | b01 |  |  | Run Semrush Backlink Gap vs 5 competitors | Needs API units allocated first
B02 | B | Unlinked brand mention reclamation | Easy | 2 | Not started | [5 empty] | n/a | n/a | varies |  | b02 |  |  | Set up brand monitoring alerts | Weekly 1 hour ongoing
A01 | A | AlternativeTo | Very easy | 3 | Not started |  |  | https://alternativeto.net/software/boldsign/ |  | Electronic Signature, Document Signing, Contract Management, PDF Signing, SaaS | Angle 1 cost | DocuSign, PandaDoc, SignWell, DocHub, DottedSign | nofollow |  | a01 |  |  | Claim listing and map alternatives | Check Inkless presence first
A11 | A | G2 optimisation and review campaign | Easy | 4 | Not started |  |  | https://www.g2.com/products/boldsign/reviews |  | Electronic Signature, Digital Signature | n/a review surface | DocuSign, PandaDoc, SignNow, Dropbox Sign, Zoho Sign, Adobe, Inkless | nofollow | 278 | a11 |  |  | Merge weak duplicate API listing then launch review push | Do not paste review count into static copy
A12a | A | Capterra | Easy | 5 | Not started |  |  |  |  | Electronic Signature, Document Management, Contract Management | Angle 5 SMB | DocuSign, PandaDoc, SignNow, Signeasy | nofollow |  | a12a |  |  | Claim vendor profile | Gartner Digital Markets requires pricing accuracy
A12b | A | GetApp | Easy | 5 | Not started |  |  |  |  | Electronic Signature, Document Management | Angle 5 SMB | DocuSign, PandaDoc, SignNow | nofollow |  | a12b |  |  | Claim vendor profile | Sync facts with Capterra but vary wording
A12c | A | Software Advice | Easy | 5 | Not started |  |  |  |  | Electronic Signature, Document Management | Angle 5 SMB | DocuSign, PandaDoc, SignNow | nofollow |  | a12c |  |  | Claim vendor profile
A29a | A | NuGet package pages | Very easy | 6 | Not started |  |  |  |  | .NET SDK | Angle 3 developer | DocuSign, Dropbox Sign | nofollow |  | a29a |  |  | Populate project URL docs URL and repo fields | Syncfusion .NET audience already here
A29b | A | npm package pages | Very easy | 6 | Not started |  |  |  |  | Node SDK | Angle 3 developer | DocuSign, Dropbox Sign | nofollow |  | a29b |  |  | Populate homepage repository keywords
A29c | A | PyPI package pages | Very easy | 6 | Not started |  |  |  |  | Python SDK | Angle 3 developer | DocuSign | nofollow |  | a29c |  |  | Populate Project URLs block
A29d | A | Maven Central | Very easy | 6 | Not started |  |  |  |  | Java SDK | Angle 3 developer | DocuSign | nofollow |  | a29d |  |  | Populate POM url and scm
A29e | A | Packagist | Very easy | 6 | Not started |  |  |  |  | PHP SDK | Angle 3 developer | DocuSign | nofollow |  | a29e |  |  | Populate composer.json homepage
A14 | A | GitHub org and repo optimisation | Easy | 7 | Not started |  |  | https://github.com/boldsign |  | Developer | Angle 3 developer | DocuSign org, DocuSign OpenAPI specs | nofollow |  | a14 |  |  | Pin MCP and SDK repos add topics
B05 | B | Free tool roundup outreach | Easy-medium | 8 | Not started | [5 empty] | n/a | n/a | do-follow target |  | b05 |  |  | Build roundup target list per tool | Prioritise no-signup tools
A02 | A | SourceForge | Very easy | 9 | Not started |  |  |  |  | Electronic Signature, Document Management, Contract Management, Workflow Management | Angle 5 SMB | DocuSign, PandaDoc, Zoho Sign | partial do-follow |  | a02 |  |  | Create vendor account and submit
A03 | A | Slashdot | Very easy | 10 | Not started |  |  |  |  | Same as SourceForge | Angle 1 cost | DocuSign, PandaDoc, SignNow | mirrors SourceForge |  | a03 |  |  | Reuse SourceForge assets vary copy
A04 | A | SaaSHub | Very easy | 11 | Not started |  |  |  |  | eSignature, Document Management, Contract Management, Legal Tech | Angle 1 cost | PandaDoc, DocuSign, Dropbox Sign, SignNow, Adobe | nofollow |  | a04 |  |  | Claim or submit then add to alternative pages
A08 | A | Crunchbase | Easy | 12 | Not started |  |  |  |  | Electronic Signature, SaaS, Document Management, Developer APIs | Angle 5 SMB | DocuSign, PandaDoc, SignNow | nofollow |  | a08 |  |  | Create as Syncfusion product entity | Link parent org
A09 | A | LinkedIn showcase and Products tab | Easy | 13 | Not started |  |  | https://www.linkedin.com/showcase/bold-sign-app |  | Software Development | Angle 2 compliance | DocuSign, PandaDoc, OneSpan | nofollow |  | a09 |  |  | Update tagline about and parent company link | Products tab is separate from showcase
B06 | B | Broken link building on rebrand wave | Medium | 14 | Not started | [5 empty] | n/a | HelloSign, Eversign, SignRequest, EchoSign | do-follow target |  | b06 |  |  | Run dead URL analysis on rebranded domains | Highest conversion outreach angle
B07 | B | Journalist response programme | Easy | 15 | Not started | [5 empty] | n/a | n/a | do-follow target |  | b07 |  |  | Set up Featured Qwoted SourceBottle alerts | Needs named spokesperson
A31 | A | MCP registries expanded | Easy-medium | 16 | Not started |  |  |  |  | AI Agents | Angle 6 AI | DocuSign API | mixed |  | a31 |  |  | Verify each registry is live then submit | Cross-check llms.txt MCP config block
A13 | A | TrustRadius | Easy-medium | 17 | Not started |  |  |  |  | Electronic Signature | Angle 2 compliance | DocuSign, PandaDoc, SignNow | nofollow |  | a13 |  |  | Submit vendor request
A16 | A | Pabbly Connect cross-link | Easy | 18 | Not started |  |  | https://www.pabbly.com/connect/integrations/boldsign/ |  | Integration | Angle 4 workflow | DocuSign, PandaDoc, Zoho Sign | nofollow |  | a16 |  |  | Confirm live then request copy refresh | Already live
B10 | B | Partner co-marketing links | Easy-medium | 19 | Not started | [5 empty] | n/a | n/a | do-follow target |  | b10 |  |  | Audit partner pages for existing links | Include Syncfusion partner network
A15 | A | Postman public collection | Medium | 20 | Not started |  |  |  |  | Developer | Angle 3 developer | DocuSign public workspace, Signeasy API | nofollow |  | a15 |  |  | Create workspace and publish | Submit to API Network
A17 | A | Zapier templates and optimisation | Medium | 21 | Not started |  |  | https://zapier.com/apps/boldsign/integrations |  | Signatures | Angle 4 workflow | DocuSign, SignNow, SignWell, Zoho Sign, XodoSign | nofollow |  | a17 |  |  | Publish 5 Zap templates | Already live
A18 | A | HubSpot Marketplace | Medium | 22 | Not started |  |  |  |  | CRM | Angle 4 workflow | DocuSign, PandaDoc, Dropbox Sign | nofollow |  | a18 |  |  | Refresh screenshots and use cases | Already live. Pursue certification
A19 | A | Salesforce AppExchange | Medium | 23 | Not started |  |  |  |  | CRM | Angle 4 workflow | DocuSign, PandaDoc, Adobe | nofollow |  | a19 |  |  | Refresh assets and collect reviews | Already live
A23 | A | AI tool directories | Easy-medium | 24 | Not started |  |  |  |  | Productivity, Business, Legal, Document Automation, AI Agents | Angle 6 AI | PandaDoc, DocuSign, Jotform | varies |  | a23 |  |  | Submit to Futurepedia Toolify TAAFT
A33 | A | Second-tier directories | Easy | 25 | Not started |  |  |  |  | Electronic Signature | Angle 5 SMB | Tier 1 | varies |  | a33 |  |  | Verify free listing before spending time | Tekpon SaaSworthy GoodFirms Crozdesk Trustpilot Gartner Peer Insights
B03 | B | Legality reference build out | Medium | 26 | Not started |  |  | https://www.boldsign.com/electronic-signature-legality/ |  |  | n/a | n/a | do-follow target |  | b03 |  |  | Add per-jurisdiction detail and last reviewed dates | CollectionPage schema already live
B04 | B | eSignature statistics page | Medium | 27 | Not started | [5 empty] | n/a | n/a | do-follow target |  | b04 |  |  | Source every figure and add original data | Highest yield passive format
B11 | B | Developer content and canonicals | Easy-medium | 28 | Not started | [5 empty] | Angle 3 developer | n/a | varies |  | b11 |  |  | Stack Overflow answers and Dev.to with canonical
A10 | A | Wikidata via Syncfusion item | Medium | 29 | Not started | [5 empty] | Neutral description | DocuSign Q5287613 | n/a |  | a10 |  |  | Add BoldSign as product statement on Syncfusion item first | Do not create standalone item without secondary sources
A05 | A | SlideShare once only | Very easy | 30 | Not started | [5 empty] | Angle 1 cost | DocuSign, Adobe, PandaDoc | nofollow |  | a05 |  |  | Upload one genuinely useful deck | Demoted from priority 5
A20 | A | Make integration | Medium | 31 | Not started |  |  |  |  | Automation | Angle 4 workflow | DocuSign, PandaDoc, Zoho Sign | nofollow |  | a20 |  |  | Feasibility check first
A21 | A | n8n integration or community node | Medium | 32 | Not started |  |  |  |  | Automation | Angle 4 workflow | DocuSign, Dropbox Sign, SignNow | nofollow |  | a21 |  |  | Community node first if official is slow
B08 | B | Guest contributions | Medium | 33 | Not started | [5 empty] | n/a | n/a | do-follow target |  | b08 |  |  | Build target publication list | Never accept paid placement
A32 | A | Product Hunt launch | Medium | 34 | Not started | [5 empty] | Angle 5 SMB | Documenso | nofollow |  | a32 |  |  | Pick discrete asset to launch not core platform | Replaces AppSumo
A26 | A | Slack App Directory | Difficult | 35 | Not started |  |  |  |  | Workflow | Angle 4 workflow | DocuSign, PandaDoc, Dropbox Sign | nofollow |  | a26 |  |  | Scope notification MVP
A27 | A | WordPress.org plugin | Difficult | 36 | Not started |  |  |  |  | Plugin | Angle 5 SMB | Formstack, Jotform, WP E-Signature | varies |  | a27 |  |  | Scope form to template workflow
B09 | B | Original research | Difficult | 37 | Not started | [5 empty] | n/a | n/a | do-follow target |  | b09 |  |  | Pick one narrow question | Highest link yield per asset
P01 | A | Google Workspace Marketplace | Difficult | Parallel | Not started | [5 empty] | Angle 4 workflow | DocuSign, PandaDoc, Dropbox Sign, SignNow, Adobe, Formstack | nofollow |  | p01 |  |  | Week 1 scoping conversation with engineering | Highest priority marketplace gap. Target month 3
P02 | A | Microsoft AppSource and Teams | Difficult | Parallel | Not started | [5 empty] | Angle 4 workflow | DocuSign, Adobe Acrobat Sign | nofollow |  | p02 |  |  | Week 2 scoping | Closest to Syncfusion existing ecosystem
X01 | A | Scribd | n/a | Dropped | Dropped | [5 empty] | n/a | n/a | nofollow |  |  |  |  | Do not pursue | Near zero value. Duplicate asset risk
X02 | A | Issuu | n/a | Dropped | Dropped | [5 empty] | n/a | n/a | nofollow |  |  |  |  | Do not pursue | Near zero value. Duplicate asset risk
X03 | A | AppSumo | n/a | Dropped | Dropped | [5 empty] | n/a | n/a | nofollow |  |  |  |  | Do not pursue | Lifetime deal contradicts unlimited envelope pricing position

## Baseline and KPIs
Baseline metrics and success criteria
Fill the yellow baseline column before week 1, then re-measure at day 30, 60, 90.
Metric | Baseline | Day 30 | Day 60 | Day 90 | Source
EXAMPLE ROW, delete: Referring domains (root) | 412 | 428 | 445 | 470 | Semrush
Referring domains (root) |  |  |  |  | Semrush / Ahrefs
Do-follow referring domains |  |  |  |  | Semrush / Ahrefs
Authority Score |  |  |  |  | Semrush
Referring domains gained, trailing 90d |  |  |  |  | Semrush
Referring domains lost, trailing 90d |  |  |  |  | Semrush
Branded impressions, trailing 28d |  |  |  |  | GSC
Referral sessions from listing surfaces |  |  |  |  | GA4
G2 review count |  |  |  |  | G2 dashboard
Capterra review count |  |  |  |  | Capterra dashboard
Live directory and marketplace profiles |  |  |  |  | This tracker
Unlinked brand mentions outstanding |  |  |  |  | Semrush / Google alerts
Success criteria at day 90
1. Workstream A: 25 or more live profiles, all facts accurate, all logged in the tracker.
2. Workstream B: 15 or more new do-follow referring domains from editorial or partner sources.
3. Review surfaces: G2 plus 15 net new reviews, Capterra plus 10 net new reviews.
4. Zero inaccurate pricing or compliance claims on any live profile.
5. Syncfusion cross-link path restored and verified in GSC.

## Competitor Gap
Competitor referring domain gap
Fill after Semrush API units are restored. This decides Workstream B priority order.
Domain | Referring domains | Authority Score | Gap vs BoldSign
boldsign.com |  |  | baseline
docusign.com
pandadoc.com
signnow.com
signwell.com
dropbox.com/sign
zoho.com/sign
Note: Semrush returned no data during preparation because this account is out of API units. Ask the account owner to allocate more before running the gap analysis.

## Claims Control
Claims control: version the pasted facts
When one number changes, every profile carrying it goes stale. Own the change here.
Claim | Current value | Verified on | Owner | Next review | Used on (profiles)
Business plan price | from $15/user/month
Free plan allowance | 25 envelopes/month
Unlimited envelopes claim | Business plan and above
Customer count | 50,000+ businesses
Country count | 120+ countries
G2 rating and volume | 4.7 from 278 reviews
G2 badges | Six Leader badges, 2026
Compliance set | SOC 2 Type II, HIPAA, GDPR, PCI DSS, eIDAS, ESIGN, UETA
Data residency | US, EU, CA, AU
Rules
1. Never paste a review count or star rating into a static third-party description.
2. Never state a competitor price on a profile you control.
3. Trusted-by and country counts must trace to a legal-approved source.
4. When any row changes, the owner sweeps every profile in Used on within 14 days.
5. Prefer from $15/user/month over $15/user/month so the claim survives plan changes.

## Bio Library
Bio library: six angles, no overlap
Copy exact. Never run the same angle on two competing surfaces in one category.
Angle and where to use | Long form, paste exact | Short form, 160 characters or under
Angle 1 Cost and volume Use on AlternativeTo, SaaSHub, Slashdot, deal and comparison surfaces | Most eSignature tools charge per envelope, so costs climb the moment a team starts sending real volume. BoldSign removes that ceiling: the Business plan includes unlimited envelopes from $15 per user per month, and a free plan covers low-volume teams. Built by Syncfusion, it handles sending, signing, tracking, templates, and audit trails without volume penalties. | eSignature software with unlimited envelopes from $15 per user per month, plus a free plan. Built by Syncfusion.
Angle 2 Compliance and security Use on TrustRadius, Gartner Peer Insights, enterprise and legal surfaces | BoldSign is an electronic signature platform built for teams that have to defend a signed document later. Every envelope carries a tamper-evident audit trail, signer authentication options, and AES-256 encryption at rest. The platform supports SOC 2 Type II, HIPAA, GDPR, PCI DSS, ESIGN, UETA, and eIDAS requirements, with data residency in the US, EU, Canada, and Australia. | Secure eSignatures with tamper-evident audit trails, signer authentication, and SOC 2 Type II, HIPAA, GDPR, and eIDAS support.
Angle 3 Developer and API Use on GitHub, Postman, package registries, RapidAPI, developer directories | BoldSign gives developers a REST API, official SDKs, webhooks, and embedded signing so signature workflows live inside the product rather than beside it. Create documents from templates, drop signing into your own UI, and react to signing events in real time. A free sandbox is available for integration work before you commit to a plan. | eSignature APIs, SDKs, webhooks, and embedded signing with a free developer sandbox.
Angle 4 CRM and operations workflow Use on HubSpot, Salesforce, Zapier, Make, n8n, Pabbly, Workspace, AppSource, Slack | BoldSign connects signature requests to the systems your team already works in. Trigger a document from a closed-won deal, a submitted form, or an approved quote, then push status back so nobody chases a signature manually. Sales, HR, and operations teams use it for contracts, offer letters, NDAs, and onboarding paperwork. | Send, track, and manage signature requests from your CRM, forms, and automation tools.
Angle 5 SMB and ease of use Use on Capterra, GetApp, Software Advice, SourceForge, Trustpilot, Product Hunt | Small teams do not need an enterprise rollout to start signing documents. BoldSign lets you upload a document, place fields, and send it for signature in minutes, then reuse it as a template. A free plan covers occasional signing, and paid plans lift the volume cap without per-envelope charges. | Upload, place fields, send. Reusable templates and a free plan for low-volume signing.
Angle 6 AI and agents Use on MCP registries, Futurepedia, Toolify, TAAFT, AI directories | BoldSign exposes its signature workflows through an MCP server, so AI assistants and agent frameworks can send documents, check signing status, and manage templates as tool calls. Teams building agentic workflows can put a legally binding signature step inside an automated process rather than breaking out to a human handoff. | An MCP server that lets AI assistants send, track, and manage legally binding signature requests.

## Priority Order
Revised priority order
Workstream A is coverage. Workstream B is authority. Run both in parallel.
Order | Action | Stream | Difficulty | Speed | Real value
0 | Syncfusion disavow fix and cross-links | B | Very easy | Same day | Recovers existing authority
1 | B1 referring domain gap analysis | B | Easy | Same day | Determines all outreach
2 | B2 unlinked mention reclamation | B | Easy | Ongoing | Do-follow, fastest wins
3 | AlternativeTo | A | Very easy | Same day | Alternative discovery
4 | G2 optimisation and review campaign | A | Easy | Ongoing | Review trust, comparison visibility
5 | Capterra, GetApp, Software Advice | A | Easy | 1 day | High-intent buyer referral
6 | Package registry cleanup, action 29 | A | Very easy | 2 hours | Developer discovery
7 | GitHub org and repo optimisation | A | Easy | Same day | Developer, LLM visibility
8 | B5 free tool roundup outreach | B | Easy-medium | 1 week | Do-follow
9 | SourceForge | A | Very easy | Same day | Directory backlink
10 | Slashdot | A | Very easy | Same day | Directory backlink
11 | SaaSHub | A | Very easy | Same day | Alternative pages
12 | Crunchbase | A | Easy | 1 day | Entity citation
13 | LinkedIn showcase and Products tab | A | Easy | Same day | Entity, brand SERP
14 | B6 broken link building | B | Medium | 1 week | Do-follow
15 | B7 journalist response programme | B | Easy | Ongoing | Editorial do-follow
16 | MCP registries, expanded, action 31 | A | Easy-medium | 3 hours | AI ecosystem
17 | TrustRadius | A | Easy-medium | 1 to 2 days | Mid-market trust
18 | Pabbly cross-link | A | Easy | Same day | Integration citation
19 | B10 partner co-marketing links | B | Easy-medium | 1 week | Contextual do-follow
20 | Postman public collection | A | Medium | Half day | API discovery
21 | Zapier templates and optimisation | A | Medium | 1 day | Marketplace referral
22 | HubSpot listing optimisation | A | Medium | 1 day | CRM marketplace
23 | Salesforce AppExchange optimisation | A | Medium | 1 day | Enterprise marketplace
24 | AI tool directories | A | Easy-medium | 1 to 2 days | AI discovery
25 | Second-tier directories, action 33 | A | Easy | Ongoing | Long-tail comparison
26 | B3 legality reference build | B | Medium | 2 to 3 weeks | Compounding editorial
27 | B4 statistics page | B | Medium | 1 to 2 weeks | Compounding editorial
28 | B11 developer content | B | Easy-medium | Ongoing | Developer domains
29 | Wikidata, via Syncfusion item first | A | Medium | Several days | Knowledge Graph
30 | SlideShare, once only | A | Very easy | Same day | Low
31 | Make integration | A | Medium | Days to weeks | Automation marketplace
32 | n8n integration or community node | A | Medium | Days to weeks | Developer, no-code
33 | B8 guest contributions | B | Medium | Per placement | Editorial do-follow
34 | Product Hunt launch, action 32 | A | Medium | 2 weeks prep | Referral spike, reviews
35 | Slack App Directory | A | Difficult | Weeks | Workflow marketplace
36 | WordPress.org plugin | A | Difficult | 2 to 4 weeks | Plugin directory authority
37 | B9 original research | B | Difficult | 6 to 10 weeks | Highest link yield
Parallel track, own milestone dates, not in the sequence above
Track | Action | Start | Target live
P1 | Google Workspace Marketplace | Week 1 scoping | Month 3
P2 | Microsoft AppSource and Teams | Week 2 scoping | Month 3 to 4
Dropped: Scribd, Issuu, AppSumo. See the patch document demote list for reasoning.

## Schedule
Execution schedule and capacity
Honest total is 70 to 90 hours plus ongoing outreach. At 8 hours a week this is a 5 to 6 month plan.
Week | Focus | Actions | Hours | Owner
1 | Foundation and fastest wins | Action 0, B1, baseline capture, AlternativeTo, package registries | 8
1 | Parallel kickoff | P1 Workspace scoping conversation | 1
2 | Review surfaces | G2 optimisation, Capterra, GetApp, Software Advice, review campaign launch | 8
3 | Directories and entity | SourceForge, Slashdot, SaaSHub, Crunchbase, LinkedIn | 7
4 | Developer and AI | GitHub, MCP registries, Postman, AI directories | 8
5 | Outreach engine on | B2 mention reclamation, B5 free tool roundups, B7 alerts live | 8
6 | Integration marketplaces | Pabbly, Zapier templates, HubSpot, Salesforce | 8
7 | Earned links | B6 broken link building, B10 partner links | 8
8 | Content assets begin | B3 legality reference scope and first tranche | 8
9 to 12 | Content assets and long tail | B3 completion, B4 statistics page, second-tier directories, TrustRadius | 32
Month 4+ | Builds and research | Slack, WordPress, Make, n8n, B8, B9, Product Hunt | ongoing
Ongoing weekly commitments, separate from the table above
Commitment | Time
B2 mention sweep | 1 hour weekly
B7 journalist responses | 3 hours weekly
Review campaign follow-up | 1 hour weekly
Reddit calendar, existing programme | per existing calendar
Tracker hygiene | 30 minutes weekly
Total maintenance | 5.5 hours weekly, budget before adding new actions
Review gates
Gate | When | Criteria
G1 | End of week 1 | Baseline captured, Action 0 complete, B1 list of 100 exported
G2 | End of week 4 | 12 or more profiles live, all claims verified, zero inaccurate pricing
G3 | End of week 8 | 5 or more new do-follow referring domains from Workstream B
G4 | Day 90 | Full success criteria from the Baseline tab
Escalate to Meikandan at any gate that misses by more than 25 percent.

## UTM Convention
UTM convention
Lowercase, hyphens only, no spaces. Build the GA4 filter before week 1.
Pattern: ?utm_source=[platform-slug]&utm_medium=[medium]&utm_campaign=link-authority-2026&utm_content=[action-id]
Medium | Use for
listing | Directories and software listings
review | G2, Capterra, GetApp, Software Advice, TrustRadius, Trustpilot
marketplace | HubSpot, Salesforce, Workspace, AppSource, Slack, Zapier, Make, n8n, Pabbly
developer | GitHub, Postman, package registries, MCP registries
community | Reddit, forums, Stack Overflow, community replies
earned | Workstream B editorial placements
Examples
https://www.boldsign.com/?utm_source=alternativeto&utm_medium=listing&utm_campaign=link-authority-2026&utm_content=a01
https://developers.boldsign.com/?utm_source=nuget&utm_medium=developer&utm_campaign=link-authority-2026&utm_content=a29
https://www.boldsign.com/free-tools/merge-pdf/?utm_source=[publisher]&utm_medium=earned&utm_campaign=link-authority-2026&utm_content=b05
Rules
1. Never put a UTM on a link you want to pass equity. Use UTMs on nofollow referral surfaces only.
2. Never UTM a link inside a Wikidata or Wikipedia reference.
3. Build a GA4 exploration filtered to utm_campaign=link-authority-2026 before week 1.

## Do Not Do
Do not do: non-negotiable
Anything here creates risk that outweighs any link gained.
# | Prohibition
1 | No paid links, sponsored do-follow placements, or guest post for a fee arrangements. If a site quotes a price for a link, walk away or require rel=sponsored.
2 | No link marketplaces, PBNs, or link packages from freelance marketplaces.
3 | No fake reviews, incentivised reviews outside the platform official programme, employee reviews posing as customers, or competitor review manipulation.
4 | No fake AlternativeTo likes, no vote manipulation, no sockpuppet accounts on any surface.
5 | No sitewide footer or nav cross-link between syncfusion.com and boldsign.com. Contextual in-content links only.
6 | No spun or near-duplicate descriptions across directories. Use the six angles in the Bio Library.
7 | No exact-match commercial anchor above 3 percent of the acquired profile.
8 | No undisclosed vendor participation in any community thread. Disclose in the first sentence, every time.
9 | No stating competitor pricing on any third-party profile you control.
10 | No compliance claim that is not currently certified and evidenced. SOC 2, HIPAA, and eIDAS claims carry legal exposure.
11 | No creating a second BoldSign profile on a platform where one already exists. Claim or merge, never duplicate.
12 | No mass directory submission tools or automated blast services.
13 | No recreating a deleted Wikidata or Wikipedia item.
14 | No lifetime deal or perpetual licence offer on any deal platform.